## Sheet1
Step Number | Description | Notes | Date
1 | Finish Github cleanup
2 | Create a robust digikey cart that doesn't disapper. Export periodically | Have an extra cart that includes interesting parts |  | Wed ID: 305426708
3 | Schematic for ADC
4 | Schematic for DAC
5 | Layout ADCs
6 | Layout DAC
7 | Setup UCF and continuously update | Actually connect on schematic Track I/O to determine if expanders are needed Will use Python code to synchronize board and UCF
8 | Design Power Supplies and power supply system
9 | Total up power and current
10 | Select and add monitoring ADC
11 | Select and add low BW DAC
12 | Add level shifters
13 | Link to ADC simulations and voltage ranges
14 | DAC amplifier -- bipolar
15 | Output connectors: SMA and pins
16 | Create a block diagram | Start by hand, created draw.io version